## Data Entry
STATISTICAL DATA ENTRY
Enter Name of Lab Personnel |  | Divisions | Sections | Urgency
1 | Gwaza | Engineering Technology Division | Engineering & Materials | Normal
2 | Nzima | Food Technology Division | ISSU | Express
3 | Mhango | Chemical Technology Division | Microbiology | In-situ
4 | Barnaba |  | Pesticides
5 | Liyaya |  | Petrochemicals
6 | Makiyi |  | General Chemistry
7 | Molande |  | Food
8 | Tech 1
9 | Tech 2
10 | Tech 3
11 | Tech 4
12 | Tech 5
13 | Tech 6
14 | Tech 7
15 | Tech 8
16 | Tech 9
17 | Tech 10
18 | Tech 11
19 | Tech 12
20 | Tech 13

## General Schedule
SAMPLE TRACKING AND TASKING SCHEDULE | [18 empty] | Total Amount
22600589.93
LAB ADMIN | [10 empty] | SCIENTIFIC OFFICER | [8 empty] | Status | Sample Residence (Days) | Sample In-Active Period (Days) | Deputy Director | Director
S/N | ID | Client | No. of Samples | MBS Nr. |  | Sample/Task Description | Date Received | Division | Section | Urgency | File | Catergory 1 | Catergory 2 | Technician | Planned Task Date | Actual Task Date | Report Date | Result | Amount (Mwk) |  |  |  | Remarks | Remarks
1 | IQS/17/683 | QASD | 2 | 3575 | 3576 | Clear Vanish | 2018-01-23 | Engineering Technology Division | ISSU | Normal | Non-Building | Vanish |  | Barnaba | 2018-03-02 | 2017-01-27 | 2018-01-27 |  | 0 | Reported | 4 | 38 |  |  | 197 | Dispose
2 | IQS/17/836 | Certification | 9 | 3577 | 3585 | Hydrated Lime | 2018-02-16 | Engineering Technology Division | ISSU | Normal | Non-Building | Lime | Road Construction | Barnaba | 2018-02-27 | Checked | 2018-02-27 |  |  | Reported | 11 | 11 |  |  | 173 | Dispose
3 | IQS/17/2221 | QASD | 1 | 3586 | 3586 | PVC Insulated Cable | 2018-01-23 | Food Technology Division | Microbiology | Normal | Non-Building | Insulation cables | Insulation Cables | Mhango | [6 empty] | 197 | 197 |  |  | 197 | Pending
4 | IQS/17/2201 | QASD | 9 | 3587 | 3595 | IBR Galvanised Iron Sheets | 2018-01-03 | Chemical Technology Division | Pesticides | Normal | Building | Iron Sheets |  | Barnaba | 2018-01-07 | 2018-01-11 | 2018-02-12 | Pass | 7700 | Reported | 40 | 4 |  |  | 217 | Dispose
5 | IQS/17/5428 | Clientele | 15 | 3596 | 3610 | River sand & Aggregate | 2018-02-16 | Chemical Technology Division | Petrochemicals | Normal | Building |  |  | Barnaba | [6 empty] | 173 | 173 |  |  | 173 | Pending
6 | IQS/17/2275 | QASD | 5 | 3611 | 3615 | Galvanised Iron Sheets | 2018-01-23 | Chemical Technology Division | General Chemistry | Normal | Building | Iron Sheets |  | Barnaba | 2018-01-27 | 2018-01-11 | 2018-01-27 |  |  | Reported | 4 | 4 |  |  | 197 | Dispose
7 | IQS/17/2270 | QASD | 1 | 3616 | 3616 | Galvanised Iron Sheets | 2018-02-16 | Food Technology Division | Food | Normal | Building | Iron Sheets |  | Liyaya | 2018-02-27 | 2018-01-11 | 2018-02-27 | Pass | 7700 | Reported | 11 | 11 |  |  | 173 | Dispose
8 | IQS/17/956 | QASD | 3 | 3617 | 3619 | Galvanised Iron Sheets | 2018-01-23 | Engineering Technology Division | Engineering & Materials | Normal | Building | Iron Sheets |  | Barnaba | 2018-01-27 | 2018-01-11 | 2018-01-27 | Pass | 7700 | Reported | 4 | 4 |  |  | 197 | Dispose
9 | IQS/17/2272 | QASD | 6 | 3620 | 3625 | Galvanised Iron Sheets | 2018-02-16 | Engineering Technology Division | Engineering & Materials | Normal | Building | Iron Sheets |  | Barnaba | 2018-02-27 | 2018-01-11 | 2018-02-27 | Pass | 7700 | Reported | 11 | 11 |  |  | 173 | Dispose
10 | IQS/17/2273 | QASD | 2 | 3626 | 3627 | Galvanised Iron Sheets | 2018-01-23 | Engineering Technology Division | Engineering & Materials | Normal | Building | Iron Sheets |  | Liyaya | 2018-01-27 | 2018-01-11 | 2018-01-27 | Pass | 7700 | Reported | 4 | 4 |  |  | 197 | Dispose
11 | IQS/17/2274 | QASD | 1 | 3628 | 3628 | Galvanised Iron Sheets | 2018-01-23 | Engineering Technology Division | Engineering & Materials | Normal | Building | Iron Sheets |  | Liyaya | 2018-01-27 | 2018-01-11 | 2018-01-27 | Pass | 7700 | Reported | 4 | 4 |  |  | 197 | Dispose
12 | IQS/17/511 | QASD | 25 | 3629 | 3653 | PVC 160mm | 2018-01-23 | Engineering Technology Division | Engineering & Materials | Normal | Non-Building | PVC Pipes |  | Molande | 2018-03-05 |  |  |  |  | Not Done | 197 | 41 |  |  | 197 | Pending
13 | IQS/17/518 | Certification | 30 | 3654 | 3683 | 20mm PVC Pipe | 2018-02-16 | Chemical Technology Division | General Chemistry | Normal | Non-Building | PVC Pipes |  | Liyaya | Pending |  |  |  |  | Not Done | 173 | 173 |  |  | 173 | Pending
14 | IQS/17/2580 | QASD | 5 | 3684 | 3688 | Galvanised Iron Sheets | 2018-01-23 | Chemical Technology Division | General Chemistry | Normal | Building | Iron Sheets |  | Liyaya | To Check Sample |  |  |  |  | Not Done | 197 | 197 |  |  | 197 | Pending
15 | IQS/17/1735 | QASD | 11 | 3689 | 3699 | Non metallic Conduit & Fitting | 2017-06-09 | Chemical Technology Division | General Chemistry | Normal | Building | Electric Wiring | 20mm | Liyaya | 2018-01-26 |  |  |  | 4000039 | Not Done | 425 | 231 |  |  | 425 | Pending
16 | IQS/17/2639 | QASD | 7 | 3700 | 3706 | Galvanised Iron Sheets | 2017-06-21 | Chemical Technology Division | General Chemistry | Normal | Non-Building | Iron Sheets |  | Liyaya | To Check Sample |  |  |  | 23300 | Not Done | 413 | 413 |  |  | 413 | Pending
17 | IQS/17/1264 | QASD | 36 | 3707 | 3742 | 10mm Hot Rolled Steel Bars | 2017-07-27 | Engineering Technology Division | ISSU | Normal | Building | Hot Rolled Steel Bars |  | Barnaba | To Check Sample |  |  |  | 456333 | Not Done | 377 | 377 |  |  | 377 | Pending
18 | IQS/17/1217 | Certification | 7 | 3743 | 3749 | 16mm Round Bars | 2018-01-23 | Engineering Technology Division | ISSU | Normal | Building | Steel Bars |  | Tech 1 | 2018-03-07 |  |  |  | 292924 | Not Done | 197 | 43 |  |  | 197 | Pending
19 | IQS/17/4204 | QASD | 5 | 3750 | 3754 | Galvanised Iron Sheets | 2018-02-16 | Engineering Technology Division | ISSU | Normal | Building | Iron Sheets |  | Barnaba | To Check Sample |  |  |  | 5845784 | Not Done | 173 | 173 |  |  | 173 | Pending
20 | IQS/17/4301 | QASD | 2 | 3755 | 3756 | Plastic Bags | 2018-01-23 | Engineering Technology Division | Engineering & Materials | Normal | Non-Building | Plastic bags |  | Barnaba | To Check Sample |  |  |  |  | Not Done | 197 | 197 |  |  | 197 | Pending
21 | IQS/17/3895(b) | QASD | 12 | 3757 | 3768 | Round Bars 6mm | 2018-01-23 | Engineering Technology Division | ISSU | Survey | Building | Steel Bars |  | Barnaba | To Check Sample |  |  |  |  | Not Done | 197 | 197 |  |  | 197 | Pending
22 | IQS/17/3895(a) | QASD | 7 | 3769 | 3775 | Round Bars 8mm | 2018-02-16 | Engineering Technology Division | Engineering & Materials | Survey | Building | Steel Bars |  | Barnaba | To Check Sample |  |  |  |  | Not Done | 173 | 173 |  |  | 173 | Pending
23 | IQS/17/3894 | QASD |  | 3776 |  | 12mm Deformed Bars | 2018-01-23 | Engineering Technology Division | ISSU | Normal | Building | Steel Bars |  | Barnaba | To Check Sample |  |  |  |  | Not Done | 197 | 197 |  |  | 197 | Pending
24 | IQS/17/4836 | QASD |  |  |  | R8 Round Steel Bars | 2018-02-16 | Engineering Technology Division | ISSU | Normal | Building | Steel Bars |  | Liyaya | To Check Sample |  |  |  | 2222324 | Not Done | 173 | 173 |  |  | 173 | Pending
25 | IQS/17/1733 | QASD |  |  |  | HDPE Pipe | 2018-01-23 | Food Technology Division | Food | Normal | Building | HDPE Pipe | CL10 | Molande | Pending |  |  |  |  | Not Done | 197 | 197 |  |  | 197 | Pending
26 | IQS/17/1730 | QASD |  |  |  | UPVC 110mm | 2018-01-23 | Food Technology Division | Food | Normal | Building | UPVC Pipe | CL4 | TECH 1 | 2018-03-16 |  |  |  | 346377 | Not Done | 197 | 52 |  |  | 197 | Pending
27 | IQS/17/4081 | QASD |  |  |  | 12mm Deformed Bars | 2018-02-16 | Food Technology Division | Food | Survey | Building | Steel Bars |  | Molande | To Check Sample |  |  |  | 23 | Not Done | 173 | 173 |  |  | 173 | Pending
28 | IQS/17/4079 | QASD |  |  |  | 16mm Deformed Bars | 2018-01-23 | Food Technology Division | Microbiology | Survey | Building | Steel Bars |  | Molande | To Check Sample |  |  |  | 5 | Not Done | 197 | 197 |  |  | 197 | Pending
29 | IQS/17/1743 | QASD |  |  |  | HDPE Pipe | 2018-01-23 | Food Technology Division | Microbiology | Normal | Building | HDPE Pipe | 20mm CL6 | Barnaba | Pending |  |  |  | 45 | Not Done | 197 | 197 |  |  | 197 | Pending
30 | IQS/17/1740 | QASD |  |  |  | HDPE Pipe | 2018-01-23 | Food Technology Division | Microbiology | Normal | Building | HDPE Pipe | 32mm CL10 | Barnaba | Pending |  |  |  | 52 | Not Done | 197 | 197 |  |  | 197 | Pending
31 | IQS/17/1741 | QASD |  |  |  | HDPE Pipe | 2018-01-23 | Food Technology Division | Microbiology | Normal | Building | HDPE Pipe | 32mm CL10 | TECH 2 | 2018-03-12 |  |  |  | 5 | Not Done | 197 | 48 |  |  | 197 | Pending
32 | IQS/17/1734 | QASD |  |  |  | PVC | 2018-01-23 | Food Technology Division | Food | Normal | Building | UPVC Pipe | 40mm | Barnaba | Pending |  |  |  | 24 | Not Done | 197 | 197 |  |  | 197 | Pending
33 | IQS/17/1731 | QASD |  |  |  | HDPE Pipe | 2018-01-23 | Food Technology Division | Microbiology | Normal | Building | HDPE Pipe | 32mm CL10 | Barnaba | Pending |  |  |  | 45734 | Not Done | 197 | 197 |  |  | 197 | Pending
34 | IQS/17/1732 | QASD |  |  |  | HDPE Pipe | 2018-01-23 | Food Technology Division | Food | Normal | Building | HDPE Pipe | 40mm CL6 | Barnaba | Pending |  |  |  | 6 | Not Done | 197 | 197 |  |  | 197 | Pending
35 | IQS/17/4952 | QASD |  |  |  | 12mm Deformed Bars | 2017-10-26 | Food Technology Division | Microbiology | Normal | Building | Steel Bars |  | Barnaba | 2018-01-09 | 2018-01-08 | 2018-01-11 | Pass | 14000 | Reported | 77 | 75 |  |  | 286 | Dispose
36 | IQS/17/IQS/17/4950 | QASD |  |  |  | 8mm Deformed Bars | 2017-10-26 | Food Technology Division | Food | Normal | Building | Steel Bars |  | Barnaba | 2018-01-09 | 2018-02-23 | 2018-02-26 | fail | 24624 | Reported | 123 | 75 |  |  | 286 | Dispose
37 | IQS/17/4958 | QASD |  |  |  | Supaset Cement | 2017-10-30 | Engineering Technology Division | ISSU | Normal | Building | Cement | 42.5R | Mhango | 2018-01-19 | 2017-12-15 | 2018-01-12 | fail | 51000 | Reported | 74 | 81 |  |  | 282 | Dispose
38 | IQS/17/1907 | Certification |  |  |  | Galvanised Iron Sheets | 2017-11-07 | Engineering Technology Division | ISSU | Normal | Building | Iron Sheets |  | Barnaba | 2018-01-11 | 2018-01-04 | 2018-01-05 |  | 7700 | Reported | 59 | 65 |  |  | 274 | Dispose
39 | IQS/17/1941 | QASD |  |  |  | Conrete Building Blocks | 2017-11-12 | Engineering Technology Division | ISSU | Express | Building | Concrete Blocks |  | Mhango | 2018-01-09 |  |  |  |  | Not Done | 269 | 58 |  |  | 269 | Pending
40 | IQS/17/6397 | QASD |  |  |  | Turpentine | 2017-11-13 | Engineering Technology Division | ISSU | Normal | Non-Building | Paints |  | Nzima | 2018-01-05 | 2018-01-04 | 2018-01-05 |  | 3800 | Reported | 53 | 53 |  |  | 268 | Dispose
41 | IQS/17/485 | QASD |  |  |  | Treated Wooden Poles | 2017-11-14 | Engineering Technology Division | ISSU | Insitu | Building | Wooden Poles |  | Mhango | 2018-01-05 | 2018-01-10 | 2018-01-11 | Fail | 28000 | Reported | 58 | 52 |  |  | 267 | Dispose
42 | IQS/17/484 | QASD |  |  |  | Treated Wooden Poles | 2018-01-23 | Food Technology Division | Food | Insitu | Building | Wooden Poles |  | Mhango | 2018-01-05 | 2018-01-10 | 2018-01-11 | Fail | 28000 | Reported | -12 | -18 |  |  | 197 | Dispose
43 | IQS/17/486 | QASD |  |  |  | Treated Wooden Poles | 2017-11-14 | Food Technology Division | Food | Insitu | Building | Wooden Poles |  | Barnaba | 2018-01-05 | 2018-01-10 | 2018-01-11 | Fail | 28000 | Reported | 58 | 52 |  |  | 267 | Dispose
44 | IQS/17/487 | QASD |  |  |  | Treated Wooden Poles | 2017-11-14 | Food Technology Division | Food | Insitu | Building | Wooden Poles |  | Barnaba | 2018-01-05 | 2018-01-10 | 2018-01-11 | Pass | 28000 | Reported | 58 | 52 |  |  | 267 | Dispose
45 | IQS/17/1942 | QASD |  |  |  | Conrete Building Blocks | 2017-11-21 | Food Technology Division | Food | Express | Building | Concrete Blocks |  | Mhango | 2018-01-09 | 2018-02-20 | 2018-02-21 | Pass | 17190.34 | Reported | 92 | 49 |  |  | 260 | Dispose
46 | IQS/17/6925 | QASD |  |  |  | Fasta | 2018-01-23 | Chemical Technology Division | General Chemistry | Normal | Building | Cement | 32.5N | Barnaba | 2018-02-26 | 2018-02-26 |  |  | 246247 | In Progress | 197 | 34 |  |  | 197 | Pending
47 | IQS/17/6616 | QASD |  |  |  | Fasta | 2017-12-05 | Chemical Technology Division | General Chemistry | Normal | Building | Cement | 32.5R | Mhango | 2018-01-16 | 2018-01-16 | 2018-02-15 | Pass | 43800 | Reported | 72 | 42 |  |  | 246 | Dispose
48 | IQS/17/6615 | QASD |  |  |  | Supaset Cement | 2017-12-05 | Chemical Technology Division | General Chemistry | Normal | Building | Cement | 42.5N | Mhango | 2018-01-16 | 2018-01-16 | 2018-02-15 | fail | 51000 | Reported | 72 | 42 |  |  | 246 | Dispose
49 | IQS/17/6614 | QASD |  |  |  | Twiga Cement | 2017-12-05 | Food Technology Division | Food | Normal | Building | Cement | 42.5N | Mhango | 2018-01-16 | 2018-01-16 | 2018-02-15 | Pass | 51000 | Reported | 72 | 42 |  |  | 246 | Dispose
50 | IQS/17/6592 | QASD |  |  |  | Galvanised Iron Sheets | 2018-01-23 | Food Technology Division | Food | Normal | Building | Iron Sheets | 32 gauge | Barnaba | 2018-01-11 | 2018-01-04 | 2018-01-05 | Pass | 7700 | Reported | -18 | -12 |  |  | 197 | Dispose
51 | IQS/17/6593 | Certification |  |  |  | Galvanised Iron Sheets | 2017-12-05 | Food Technology Division | Food | Normal | Building | Iron Sheets | 32 gauge | Barnaba | 2018-01-11 | 2018-01-04 | 2018-01-05 |  | 7700 | Reported | 31 | 37 |  |  | 246 | Dispose
52 | IQS/17/6594 | QASD |  |  |  | Galvanised Iron Sheets | 2017-12-05 | Food Technology Division | Microbiology | Normal | Building | Iron Sheets | 32 gauge | Barnaba | 2018-01-11 | 2018-01-11 | 2018-01-12 | Pass | 33770 | Reported | 38 | 37 |  |  | 246 | Dispose
53 | IQS/17/6595 | QASD |  |  |  | Galvanised Iron Sheets | 2017-12-05 | Food Technology Division | Food | Normal | Building | Iron Sheets | 32 gauge | Mhango | 2018-01-11 | 2018-01-11 | 2018-01-12 | Pass | 7700 | Reported | 38 | 37 |  |  | 246 | Dispose
54 | IQS/17/6573 | QASD |  |  |  | Supaset Cement | 2017-12-07 | Engineering Technology Division | Engineering & Materials | Normal | Building | Cement | 42.5N | Mhango | 2017-12-12 | 2017-12-12 | 2018-01-09 | Pass | 5666965 | Reported | 33 | 5 |  |  | 244 | Dispose
55 | IQS/17/6571 | QASD |  |  |  | Twiga Cement | 2017-12-07 | Chemical Technology Division | General Chemistry | Normal | Building | Cement | 42.5N | Mhango | 2018-01-25 | 2018-01-25 |  |  | 34657 | In Progress | 244 | 49 |  |  | 244 | Pending
56 | IQS/17/6977 | QASD |  |  |  | Gumboots | 2017-12-07 | Chemical Technology Division | Petrochemicals | Normal | Non-Building | Footwear |  | Nzima | 2018-01-05 | 2018-01-05 | 2018-01-05 | Pass | 4800 | Reported | 29 | 29 |  |  | 244 | Dispose
57 | 1991 | QASD |  |  |  | Non metallic Conduit & Fitting | 2017-12-08 | Chemical Technology Division | Pesticides | Normal | Building | Electric Wiring |  | Barnaba | 2018-01-26 |  |  |  | 63457 | Not Done | 243 | 49 |  |  | 243 | Pending
58 | 1992 | QASD |  |  |  | Non metallic Conduit & Fitting | 2017-12-08 | Engineering Technology Division | Engineering & Materials | Normal | Building | Electric Wiring |  | Barnaba | 2018-01-26 |  |  |  | 45647 | Not Done | 243 | 49 |  |  | 243 | Pending
59 | 1982 | QASD |  |  |  | Solvent Cement | 2017-12-08 | Engineering Technology Division | Engineering & Materials | Normal | Building |  |  | Nzima | 2018-01-05 | 2018-01-05 | 2018-01-05 |  | 59796 | Reported | 28 | 28 |  |  | 243 | Dispose
60 | 6622 | QASD |  |  |  | 10mm Deformed Bars | 2017-12-08 | Engineering Technology Division | Engineering & Materials | Normal | Building | Steel Bars |  | Mhango | 2018-01-09 | 2018-01-11 | 2018-01-12 | Pass | 14000 | Reported | 35 | 32 |  |  | 243 | Dispose
61 | 6627 | QASD |  |  |  | 20mm Deformed Bars | 2017-12-08 | Engineering Technology Division | Engineering & Materials | Normal | Building | Steel Bars |  | Mhango | 2018-01-09 | 2018-01-04 | 2018-01-05 |  | 14000 | Reported | 28 | 32 |  |  | 243 | Dispose
62 | 6621 | QASD |  |  |  | 20mm Deformed Bars | 2017-12-08 | Engineering Technology Division | Engineering & Materials | Normal | Building | Steel Bars |  | Barnaba | 2018-01-09 | 2018-01-04 | 2018-01-05 |  | 14000 | Reported | 28 | 32 |  |  | 243 | Dispose
63 | 6620 | QASD |  |  |  | 8mm Deformed Bars | 2017-12-08 | Engineering Technology Division | Engineering & Materials | Normal | Building | Steel Bars |  | Barnaba | 2018-01-09 | 2018-01-11 | 2018-01-12 | Pass | 14000 | Reported | 35 | 32 |  |  | 243 | Dispose
64 | 6625 | QASD |  |  |  | 16mm Deformed Bars | 2017-12-08 | Engineering Technology Division | Engineering & Materials | Normal | Building | Steel Bars |  | Mhango | 2018-01-09 | 2018-01-04 | 2018-01-05 |  | 14000 | Reported | 28 | 32 |  |  | 243 | Dispose
65 | 6626 | QASD |  |  |  | 12mm Deformed Bars | 2017-12-08 | Engineering Technology Division | Engineering & Materials | Normal | Building | Steel Bars |  | Barnaba | 2018-01-09 | 2018-01-04 | 2018-01-05 |  | 14000 | Reported | 28 | 32 |  |  | 243 | Dispose
66 | 6624 | QASD |  |  |  | 12mm Deformed Bars | 2017-12-08 | Engineering Technology Division | Engineering & Materials | Normal | Building | Steel Bars |  | Mhango | 2018-01-09 | 2018-01-04 | 2018-01-05 |  | 14000 | Reported | 28 | 32 |  |  | 243 | Dispose
67 | 6623 | QASD |  |  |  | 12mm Deformed Bars | 2017-12-08 | Chemical Technology Division | Petrochemicals | Normal | Building | Steel Bars |  | Barnaba | 2018-01-09 | 2018-01-04 | 2018-01-05 |  | 14000 | Reported | 28 | 32 |  |  | 243 | Dispose
68 | 6628 | QASD |  |  |  | 12mm Deformed Bars | 2017-12-08 | Chemical Technology Division | Petrochemicals | Normal | Building | Steel Bars |  | Mhango | 2018-01-09 | 2018-01-04 | 2018-01-05 |  | 14000 | Reported | 28 | 32 |  |  | 243 | Dispose
69 | 4678 | QASD |  |  |  | Round Hot Rolled Bars | 2017-12-09 | Chemical Technology Division | Pesticides | Normal | Building | Hot Rolled Steel Bars | 4mm | Barnaba | 2018-01-11 |  |  |  |  | Not Done | 242 | 33 |  |  | 242 | Pending
70 | 6572 | QASD |  |  |  | Fasta | 2017-12-11 | Chemical Technology Division | Pesticides | Normal | Building | Cement | 32.5R | Mhango | 2018-01-25 | 2018-01-25 |  |  | 462389 | In Progress | 240 | 45 |  |  | 240 | Pending
71 | 7032 | QASD |  |  |  | Fasta | 2017-12-16 | Chemical Technology Division | General Chemistry | Normal | Building | Cement |  | Makiyi | 2018-01-25 | 2018-01-25 |  |  |  | In Progress | 235 | 40 |  |  | 235 | Pending
72 | 7034 | QASD |  |  |  | Fasta | 2017-12-16 | Chemical Technology Division | General Chemistry | Normal | Building | Cement | 32.5R | Mhango | 2018-01-25 | 2018-01-25 |  |  |  | In Progress | 235 | 40 |  |  | 235 | Pending
73 | 7035 | QASD |  |  |  | Fasta | 2017-12-16 | Food Technology Division | Microbiology | Normal | Building | Cement | 32.5R | Mhango | 2018-01-25 | 2018-01-25 |  |  | 25646 | In Progress | 235 | 40 |  |  | 235 | Pending
74 | 7036 | QASD |  |  |  | Supaset Cement | 2017-12-16 | Chemical Technology Division | Microbiology | Normal | Building | Cement | 42.5R | Mhango | 2018-01-25 | 2018-01-25 |  |  |  | In Progress | 235 | 40 |  |  | 235 | Pending
75 | 7037 | QASD |  |  |  | CM | 2017-12-16 | Food Technology Division | Food | Normal | Building | Cement | 42.5N | Barnaba | 2018-02-26 | 2018-02-26 |  |  |  | In Progress | 235 | 72 |  |  | 235 | Pending
76 | 7033 | QASD |  |  |  | Twiga Cement | 2017-12-16 | Engineering Technology Division | ISSU | Normal | Building | Cement | 42.5N | Barnaba | 2018-02-26 | 2018-02-26 |  |  | 13531 | In Progress | 235 | 72 |  |  | 235 | Pending
77 | 7031 | QASD |  |  |  | Fasta | 2017-12-16 | Engineering Technology Division | Engineering & Materials | Normal | Building | Cement | 32.5R | Barnaba | 2018-02-26 | 2018-02-26 |  |  |  | In Progress | 235 | 72 |  |  | 235 | Pending
78 | 7038 | QASD |  |  |  | Supaset Cement | 2017-12-18 | Engineering Technology Division | ISSU | Normal | Building | Cement | 42.5R | Mhango | 2018-01-25 | 2018-01-25 |  |  |  | In Progress | 233 | 38 |  |  | 233 | Pending
79 | 6645 | QASD |  |  |  | Fasta | 2017-12-18 | Engineering Technology Division | Engineering & Materials | Normal | Building | Cement | 32.5R | Barnaba | 2018-02-26 | 2018-02-26 |  |  |  | In Progress | 233 | 70 |  |  | 233 | Pending
80 | 6646 | QASD |  |  |  | Supaset Cement | 2017-12-18 | Food Technology Division | Food | Normal | Building | Cement | 42.5R | Mhango | 2018-01-25 | 2018-01-25 |  |  |  | In Progress | 233 | 38 |  |  | 233 | Pending
81 | 7063 | QASD |  |  |  | Fasta | 2017-12-22 | Chemical Technology Division | General Chemistry | Normal | Building | Cement | 32.5R | Mhango | 2018-01-29 | 2018-01-29 | 2018-02-15 | Pass | 51000 | Reported | 55 | 38 |  |  | 229 | Dispose
82 | 7045 | QASD |  |  |  | Sanitary Towels | 2017-12-22 | Food Technology Division | Microbiology | Normal | Non-Building | Other |  | Nzima | 2018-01-05 | 2018-01-06 | 2018-01-08 |  | 10800 | Reported | 17 | 14 |  |  | 229 | Dispose
83 | 7207 | QASD |  |  |  | Euro Cem | 2017-12-27 | Food Technology Division | Microbiology | Express | Building | Cement | 32.5R | Mhango | 2018-01-16 | 2018-01-16 | 2018-02-15 | Pass | 43800 | Reported | 50 | 20 |  |  | 224 | Dispose
84 | 7208 | QASD |  |  |  | Ultra Cem | 2017-12-27 | Engineering Technology Division | ISSU | Express | Building | Cement | 52.5R | Mhango | 2018-01-16 | 2018-01-16 | 2018-02-15 | Pass | 51000 | Reported | 50 | 20 |  |  | 224 | Dispose
85 | 7229 | QASD |  |  |  | Blank Number Plates | 2017-12-28 | Chemical Technology Division | General Chemistry | Normal | Non-Building | Number Plates |  | Nzima | 2018-01-04 | 2018-01-04 | 2018-01-04 | Pass | 15221 | Reported | 7 | 7 |  |  | 223 | Dispose
86 | 7230 | QASD |  |  |  | Blank Number Plates | 2017-12-28 | Chemical Technology Division | General Chemistry | Normal | Non-Building | Number Plates |  | Makiyi | 2018-01-04 | 2018-01-04 | 2018-01-04 | Pass | 15221 | Reported | 7 | 7 |  |  | 223 | Dispose
87 | 7231 | QASD |  |  |  | Blank Number Plates | 2017-12-28 | Chemical Technology Division | General Chemistry | Normal | Non-Building | Number Plates |  | Nzima | 2018-01-04 | 2018-01-04 | 2018-01-04 | Pass | 15221 | Reported | 7 | 7 |  |  | 223 | Dispose
88 | 6638 | QASD |  |  |  | Galvanised Iron Sheets |  | Food Technology Division | Microbiology | Normal | Building | Iron Sheets |  | Mhango | 2018-01-04 | 2018-01-04 | 2018-01-05 | Pass | 7700 | Reported |  |  |  |  | 43320 | Dispose
89 | 7238 | QASD |  |  |  | Tembo Fasta | 2018-01-04 | Food Technology Division | Microbiology | Normal | Building | Cement | 32.5R | Mhango | 2018-03-05 |  |  |  |  | Not Done | 216 | 60 |  |  | 216 | Pending
90 | 7237 | Imports |  |  |  | Dangote OPC | 2018-01-04 | Engineering Technology Division | ISSU | Normal | Building | Cement | 32.5R | Mhango | 2018-03-05 |  |  |  |  | Not Done | 216 | 60 |  |  | 216 | Pending
91 | [5 empty] | Cleaning Laboratory |  | Engineering Technology Division | ISSU |  |  | General Cleaning |  | Barnaba | 2018-01-06 | 2018-01-06 | 2018-01-06 |  |  | Reported |  |  |  |  | 43320 | Dispose
92 | [5 empty] | Cleaning Laboratory |  | Engineering Technology Division | Engineering & Materials |  |  | General Cleaning |  | Barnaba | 2018-01-07 | 2018-01-07 | 2018-01-17 |  |  | Reported |  |  |  |  | 43320 | Dispose
93 | 019 | Imports |  |  |  | Trustee school Shoes | 2018-01-05 | Engineering Technology Division | Engineering & Materials | Normal | Non-Building | Shoes | Stuck non outer soles | Mhango | 2018-01-11 | 2018-01-09 | 2018-01-10 | Pass | 7049 | Reported | 5 | 6 |  |  | 215 | Dispose
94 | 015 | Imports |  |  |  | Stay Free Regular Pads | 2018-01-05 | Engineering Technology Division | Engineering & Materials | Normal | Non-Building | Sanitary Pads |  | Nzima | 2018-01-17 | 2018-01-06 | 2018-01-08 | Pass | 10800 | Reported | 3 | 12 |  |  | 215 | Dispose
95 | 020 | Imports |  |  |  | Lion Black Shoe Polish | 2018-01-05 | Engineering Technology Division | Engineering & Materials | Normal | Non-Building | Shoe Polish |  | Nzima | 2018-01-10 | 2018-01-19 | 2018-01-22 | pass | 13000 | Reported | 17 | 5 |  |  | 215 | Dispose
96 | 001 | Imports |  |  |  | Polypropylene Grain Sacks | 2018-01-05 | Food Technology Division | Microbiology | Normal | Non-Building | Grain Sacks | Monsato | mhango | 2018-01-09 | 2018-01-10 | 2018-01-11 | Pass | 5195.55 | Reported | 6 | 4 |  |  | 215 | Dispose
97 | [5 empty] | Cleaning Laboratory |  | Engineering Technology Division | ISSU |  |  | General Cleaning |  | Barnaba | 2018-01-20 | 2018-01-20 | 2018-01-20 |  |  | Reported |  |  |  |  | 43320 | Dispose
98 | [5 empty] | Cleaning Laboratory |  | Chemical Technology Division | General Chemistry |  |  | General Cleaning |  | Barnaba | 2018-01-21 | 2018-01-21 | 2018-01-21 |  |  | Reported |  |  |  |  | 43320 | Dispose
99 | 6596 | Imports |  |  |  | Galvanised Iron Sheets | 2017-12-05 | Engineering Technology Division | Engineering & Materials | Normal | Building | Iron Sheets | 32 gauge | Barnaba | 2017-01-04 | 2018-01-04 | 2018-01-05 | Pass | 7700 | Reported | 31 | -335 |  |  | 246 | Dispose
100 | AV345 | Clientele |  |  |  | Clinker, Sand and Pozolana | 2018-01-08 | Engineering Technology Division | ISSU | Express | Non-Building | Density | Lafarge | Gwaza | 2018-01-09 | 2018-01-24 | 2018-02-06 | Pass |  | Reported | 29 | 1 |  |  | 212 | Dispose
101 | SR6013 | Clientele |  |  |  | Plastic Bottles containing pesticides | 2018-01-10 | Food Technology Division | Microbiology | Normal | Non-Building | Auction Holdings Chemicals Limited | Joseph Banda | Gwaza | 2018-01-12 | 2018-01-18 | 2018-01-19 | Pass | 29241.5 | Reported | 9 | 2 |  |  | 210 | Dispose
102 | SR6014 | Clientele |  |  |  | ZCCC Supaset Cement | 2018-01-09 | Chemical Technology Division | General Chemistry | Express | Building | Cement | 42.5N | Mhango | 2018-01-16 | 2018-01-16 | 2018-02-19 | Pass | 63565.52 | Reported | 41 | 7 |  |  | 211 | Dispose
103 | SR6014 | Clientele |  |  |  | ZCCC FastaPlus | 2018-01-09 | Chemical Technology Division | Petrochemicals | Express | Building | Cement | 32.5R | Makiyi | 2018-01-16 | 2018-01-16 | 2018-02-19 | Fail | 55061.02 | Reported | 41 | 7 |  |  | 211 | Dispose
104 | 6377 | Imports |  |  |  | Ordinary Portland Cement | 2017-11-08 | Chemical Technology Division | Petrochemicals | Normal | Building | Cement | 32.5R | Mhango | 2017-12-15 | 2017-12-15 | 2018-01-12 | Pass | 43800 | Reported | 65 | 37 |  |  | 273 | Dispose
105 | 6415 | Imports |  |  |  | Ordinary Portland Cement | 2017-11-13 | Chemical Technology Division | Petrochemicals | Normal | Building | Cement | 32.5N | Mhango | 2017-12-15 | 2017-12-15 | 2018-01-12 | Pass | 43800 | Reported | 60 | 32 |  |  | 268 | Dispose
106 | 4946 | Imports |  |  |  | Ordinary Portland Cement | 2017-10-17 | Chemical Technology Division | Pesticides | Normal | Building | Cement | 32.5R | Mhango | 2017-12-15 | 2017-12-15 | 2018-01-12 | Pass | 43800 | Reported | 87 | 59 |  |  | 295 | Dispose
107 | 4945 | Imports |  |  |  | Ordinary Portland Cement | 2017-10-17 | Food Technology Division | Food | Normal | Building | Cement | 32.5R | Mhango | 2017-12-15 | 2017-12-15 | 2018-01-12 | Pass | 43800 | Reported | 87 | 59 |  |  | 295 | Dispose
108 | 6414 | Imports |  |  |  | Ordinary Portland Cement | 2017-11-13 | Food Technology Division | Food | Express | Building | Cement | 42.5R | Mhango | 2017-12-15 | 2017-12-15 | 2018-01-12 | Pass | 51000 | Reported | 60 | 32 |  |  | 268 | Dispose
109 | 4944 | Imports |  |  |  | Ordinary Portland Cement | 2017-10-17 | Food Technology Division | Food | Normal | Building | Cement | 42.5N | Mhango | 2017-12-15 | 2017-12-15 | 2018-01-12 | pass | 51000 | Reported | 87 | 59 |  |  | 295 | Dispose
110 | 6375 | Imports |  |  |  | Ordinary Portland Cement | 2017-11-08 | Engineering Technology Division |  | Normal | Building | Cement | 42.5N | Mhango | 2017-12-15 | 2017-12-15 | 2018-01-12 | Fail | 51000 | Reported | 65 | 37 |  |  | 273 | Dispose
111 | 6927 | Imports |  |  |  | Ordinary Portland Cement | 2017-11-28 | Food Technology Division |  | Normal | Building | Cement | 42.5R | Mhango | 2017-12-12 | 2017-12-12 | 2018-01-09 | Pass | 51000 | Reported | 42 | 14 |  |  | 253 | Dispose
112 | 039 | Imports |  |  |  | Wax shoe Polish | 2018-01-12 | Engineering Technology Division |  | Normal | Non-Building | Shoe Polish | Black | Nzima | 2018-01-17 | 2018-01-19 | 2018-01-22 | Fail | 13000 | Reported | 10 | 5 |  |  | 208 | Dispose
113 | 040 | Imports |  |  |  | Wax shoe Polish | 2018-01-12 | Engineering Technology Division |  | Normal | Non-Building | Shoe Polish | Kiwi Dark Tan | Makiyi | 2018-01-17 | 2018-01-19 | 2018-01-22 | Pass | 13000 | Reported | 10 | 5 |  |  | 208 | Dispose
114 | 7197 | Imports |  |  |  | Emulsion Paint | 2018-01-12 | Engineering Technology Division |  | Normal | Non-Building | Paints | Duram Wall Ceiling | Nzima | 2018-01-16 | 2018-01-18 | 2018-01-22 | Pass | 24100 | Reported | 10 | 4 |  |  | 208 | Dispose
115 | 7196 | Imports |  |  |  | Emulsion Paint | 2018-01-12 | Engineering Technology Division |  | Normal | Non-Building | Paints | Duram Water Proof Felexiwal | Nzima | 2018-01-18 | 2018-01-18 | 2018-01-22 | Pass | 24100 | Reported | 10 | 6 |  |  | 208 | Dispose
116 | 7195 | Imports |  |  |  | Emulsion Paint | 2018-01-12 | Engineering Technology Division |  | Normal | Non-Building | Paints | Duram acrylic | Nzima | 2018-01-18 | 2018-01-18 | 2018-01-22 | Pass | 24100 | Reported | 10 | 6 |  |  | 208 | Dispose
117 | 7193 | Imports |  |  |  | Emulsion Paint | 2018-01-12 | Engineering Technology Division |  | Normal | Non-Building | Paints | Roof Paint | Makiyi | 2018-01-18 | 2018-01-19 | 2018-01-22 | Pass | 20100 | Reported | 10 | 6 |  |  | 208 | Dispose
118 | IQS/18/028 | Imports |  |  |  | Treated Wooden Poles | 2018-01-16 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
119 | IQS/18/022 | Imports |  |  |  | Treated Wooden Poles 15m | 2018-01-16 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
120 | IQS/18/034 | Imports |  |  |  | Treated Wooden Poles | 2018-01-16 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
121 | IQS/18/012 | Imports |  |  |  | Treated Wooden Poles 12.3m | 2018-01-16 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
122 | IQS/18/013 | Imports |  |  |  | Treated Wooden Poles 11m | 2018-01-16 | Chemical Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
123 | IQS/18/014 | Imports |  |  |  | Treated Wooden Poles 11m | 2018-01-16 | Chemical Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Makiyi | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
124 | IQS/18/015 | Imports |  |  |  | Treated Wooden Poles 12.3m | 2018-01-16 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
125 | IQS/18/016 | Imports |  |  |  | Treated Wooden Poles 12.3m | 2018-01-16 | Engineering Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
126 | IQS/18/017 | Imports |  |  |  | Treated Wooden Poles 11m | 2018-01-16 | Chemical Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
127 | IQS/18/019 | Imports |  |  |  | Treated Wooden Poles 13.5m | 2018-01-16 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Makiyi | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
128 | IQS/18/020 | Imports |  |  |  | Treated Wooden Poles 16.5m | 2018-01-16 | Engineering Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
129 | IQS/18/021 | Imports |  |  |  | Treated Wooden Poles 16.5m | 2018-01-16 | Chemical Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-01-18 | 2018-01-18 | 2018-01-31 | pass | 28000 | Reported | 15 | 2 |  |  | 204 | Dispose
130 | 6644 | Imports |  |  |  | OPC Tembo Fatsa Plus | 2017-12-18 | Food Technology Division |  | Normal | Building | Cement | 32.5R | Mhango | 2018-01-16 | 2018-01-16 | 2018-02-15 | Pass | 43800 | Reported | 59 | 29 |  |  | 233 | Dispose
131 | 6335 | Imports |  |  |  | Amaka cement | 2017-11-08 | Engineering Technology Division |  | Normal | Building | Cement | 42.5N | Barnaba | To Check Sample | Checked | Report Date |  |  | Reported | #VALUE! | 273 |  |  | 273 | Dispose
132 | 6935 | Imports |  |  |  | Tembo Fasta Plus | 2017-11-28 | Chemical Technology Division |  | Normal | Building | Cement | 32.5N | Mhango | 2018-03-05 |  |  |  |  | Not Done | 253 | 97 |  |  | 253 | Pending
133 | 6926 | Imports |  |  |  | Lafarge Superset cement | 2017-11-28 | Food Technology Division |  | Normal | Building | Cement | 42.5N | Mhango | 2018-03-05 |  |  |  |  | Not Done | 253 | 97 |  |  | 253 | Pending
134 | AU7420 | Clientele |  |  |  | Mota Engil Cement | 2017-08-25 | Food Technology Division |  | Normal | Building | Cement |  | Barnaba | To Check Sample | Checked | Not Available |  |  | Reported | #VALUE! | 348 |  |  | 348 | Dispose
135 | 4607 | Imports |  |  |  | FasTA Plus Tembo Cement | 2016-11-21 | Chemical Technology Division |  | Normal | Building | Cement | 32.5R | Barnaba | To Check Sample | Checked | Not Available |  |  | Reported | #VALUE! | 625 |  |  | 625 | Dispose
136 | 6736 | Imports |  |  |  | Dangote OPC | 2016-11-11 | Chemical Technology Division |  | Normal | Building | Cement | 42.5R | Barnaba | To Check Sample | Checked | Not Available |  |  | Reported | #VALUE! | 635 |  |  | 635 | Dispose
137 | IQS/17/6619 | Imports |  |  |  | Surecast Cement | 2017-12-07 | Chemical Technology Division |  | Normal | Building | Cement |  | Mhango | 2017-12-10 | 2017-12-10 | 2017-12-12 | pass | 27000 | Reported | 5 | 3 |  |  | 244 | Dispose
138 | IQS/18/176 | Imports |  |  |  | Y16 Deformed Bars | 2018-01-24 | Engineering Technology Division |  | Normal | Building | Steel Bars |  | Barnaba | 2018-01-24 | 2018-01-24 | 2018-01-24 | pass | 14000 | Reported | 0 | 0 |  |  | 196 | Dispose
139 | IQS/18/175 | Imports |  |  |  | Y12 Deformed Bars | 2018-01-24 | Engineering Technology Division |  | Normal | Building | Steel Bars |  | Barnaba | 2018-01-24 | 2018-01-24 | 2018-01-24 | pass | 14000 | Reported | 0 | 0 |  |  | 196 | Dispose
140 | AV378 | Clientele |  |  |  | Gypsum | 2018-01-24 | Food Technology Division |  | Normal | Non-Building | Lafarge |  | Gwaza | 2018-01-25 | 2018-02-06 | 2018-02-06 | Pass | 7410.5 | Reported | 13 | 1 |  |  | 196 | Dispose
141 | IQS/18/193 | Imports |  |  |  | Tembo Superset Cement | 2018-01-29 | Chemical Technology Division |  | Normal | Building | Cement | 42.5N | Mhango | pending |  |  |  |  | Not Done | 191 | 191 |  |  | 191 | Pending
142 | CIS/17/1747 | Certification |  |  |  | Kulimba Cement | 2018-01-29 | Food Technology Division |  | Normal | Building | Cement | 32.5N | Mhango | 2018-02-21 | 2018-02-21 |  |  |  | In Progress | 191 | 23 |  |  | 191 | Pending
143 | IQS/18/192 | Imports |  |  |  | Tembo Superset Cement | 2018-01-29 | Engineering Technology Division |  | Normal | Building | Cement | 42.5N | Gwaza | 2018-03-01 |  |  |  |  | Not Done | 191 | 31 |  |  | 191 | Pending
144 | IQS/18/191 | Imports |  |  |  | tembo fasta cement | 2018-01-29 | Chemical Technology Division |  | Normal | Building | Cement | 32.5R | mhango | 2018-02-21 | 2018-02-21 |  |  |  | In Progress | 191 | 23 |  |  | 191 | Pending
145 | IQS/18/190 | Imports |  |  |  | tembo fasta cement | 2018-01-29 | Food Technology Division |  | Normal | Building | Cement | 32.5R | mhango | Sample not provide yet |  |  |  |  | Not Done | 191 | 191 |  |  | 191 | Pending
146 | IQS/18/018 | Imports |  |  |  | FasTA Plus Tembo Cement | 2018-01-29 | Engineering Technology Division |  |  | Building | Cement | 32.5R |  | No Lab Slip provided |  |  |  |  | Not Done | 191 | 191 |  |  | 191 | Pending
147 | IQS/18/019 | Imports |  |  |  | FasTA Plus Tembo Cement | 2018-01-29 | Engineering Technology Division |  |  | Building | Cement | 32.5R |  | No Lab Slip provided |  |  |  |  | Not Done | 191 | 191 |  |  | 191 | Pending
148 | IQS/18/037 | Imports |  |  |  | N50 Lead Acid Batteries | 2018-01-31 | Engineering Technology Division |  | Normal | Non-Building | Lead Acid Batteries | DIN 66 MFL Powerstart | Barnaba | 2018-02-02 | 2018-02-02 | 2018-02-02 | Pass | 20200 | Reported | 2 | 2 |  |  | 189 | Dispose
149 | IQS/18/038 | Imports |  |  |  | N50 Lead Acid Batteries | 2018-01-30 | Food Technology Division |  | Normal | Non-Building | Lead Acid Batteries | D45 MFL Powerstart | Barnaba | 2018-02-02 | 2018-02-02 | 2018-02-02 | Pass | 20200 | Reported | 3 | 3 |  |  | 190 | Dispose
150 | IQS/18/237 | Imports |  |  |  | N50 Lead Acid Batteries | 2018-01-31 | Chemical Technology Division |  | Normal | Non-Building | Lead Acid Batteries | Willard | Barnaba | 2018-02-02 | 2018-02-02 | 2018-02-02 | Pass | 20200 | Reported | 2 | 2 |  |  | 189 | Dispose
151 | IQS/18/236 | Imports |  |  |  | N70 Lead Acid Batteries | 2018-01-31 | Food Technology Division |  | Normal | Non-Building | Lead Acid Batteries |  | Barnaba | 2018-02-02 | 2018-02-02 | 2018-02-02 | Fail | 20200 | Reported | 2 | 2 |  |  | 189 | Dispose
152 | IQS/18/220 | Imports |  |  |  | Durata Batteries | 2018-01-31 | Engineering Technology Division |  | Express | Non-Building | R20 | Extra Heavy Duty | Barnaba | 2018-02-02 | 2018-02-02 | 2018-02-02 | Pass | 3800 | Reported | 2 | 2 |  |  | 189 | Dispose
153 | IQS/18/227 | Imports |  |  |  | Luminous 12V 150Ah | 2018-01-31 | Chemical Technology Division |  | Normal | Non-Building | Solar Batteries |  | Barnaba | 2018-02-02 | 2018-02-02 | 2018-02-02 |  | 18300 | Reported | 2 | 2 |  |  | 189 | Dispose
154 | IQS/18/120 | Imports |  |  |  | Kodak Ultra Premium | 2018-01-31 | Food Technology Division |  | Normal | Non-Building | Alkaline Batteries |  | Barnaba | 2018-02-02 | Lab Slip returned |  |  |  | In Progress | 189 | 2 |  |  | 189 | Pending
155 | IQS/18/221 | Imports |  |  |  | Durata Batteries | 2018-01-31 | Chemical Technology Division |  | Express | Non-Building | R20 | Extra Heavy Duty | Barnaba | 2018-02-02 | 2018-02-02 | 2018-02-02 | Pass | 3800 | Reported | 2 | 2 |  |  | 189 | Dispose
156 | IQS/18/223 | Imports |  |  |  | Toughees Non Polish | 2018-01-31 | Food Technology Division |  | Normal | Non-Building | School shoes | Leather Shoes | Barnaba | 2018-02-02 | 2018-02-02 | 2018-02-02 | Pass | 7049 | Reported | 2 | 2 |  |  | 189 | Dispose
157 | IQS/18/224 | Imports |  |  |  | Infants and Childrens Shoes | 2018-01-31 | Engineering Technology Division |  | Normal | Non-Building | School shoes |  | Barnaba | 2018-02-02 | 2018-02-02 | 2018-02-02 | Pass | 7049 | Reported | 2 | 2 |  |  | 189 | Dispose
158 | IQS/18/082 | Imports |  |  |  | Treated Wooden Poles | 2018-01-31 | Chemical Technology Division |  | Normal | Non-Building | Wooden Poles | Lilongwe | Mhango | 2018-02-05 | 2018-02-13 | 2018-02-19 | Pass | 28000 | Reported | 19 | 5 |  |  | 189 | Dispose
159 | IQS/18/079 | Imports |  |  |  | Treated Wooden Poles | 2018-01-31 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Lilongwe | Mhango | 2018-02-05 | 2018-02-13 | 2018-02-19 | pass | 28000 | Reported | 19 | 5 |  |  | 189 | Dispose
160 | IQS/18/084 | Imports |  |  |  | Treated Wooden Poles | 2018-01-31 | Chemical Technology Division |  | Normal | Non-Building | Wooden Poles | Lilongwe | Mhango | 2018-02-05 | 2018-02-13 | 2018-02-13 | Pass | 28000 | Reported | 13 | 5 |  |  | 189 | Dispose
161 | IQS/18/099 | Imports |  |  |  | Treated Wooden Poles | 2018-01-31 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Lilongwe | Mhango | 2018-02-05 | 2018-02-13 | 2018-02-19 | Pass | 28000 | Reported | 19 | 5 |  |  | 189 | Dispose
162 | IQS/18/088 | Imports |  |  |  | Treated Wooden Poles | 2018-01-31 | Engineering Technology Division |  | Normal | Non-Building | Wooden Poles | Lilongwe | Mhango | 2018-02-05 | 2018-02-13 | 2018-02-19 | Pass | 28000 | Reported | 19 | 5 |  |  | 189 | Dispose
163 | IQS-I/18/120 | Imports |  |  |  | Treated Wooden Poles 9m | 2018-02-01 | Engineering Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Mhango | 2018-02-05 | 2018-02-08 | 2018-02-09 | Fail | 28000 | Reported | 8 | 4 |  |  | 188 | Dispose
164 | IQS-I/18/104 | Imports |  |  |  | Treated Wooden Poles | 2018-02-01 | Engineering Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Nzima | 2018-02-05 | 2018-02-08 | 2018-02-09 | Fail | 28000 | Reported | 8 | 4 |  |  | 188 | Dispose
165 | IQS-I/18/110 | Imports |  |  |  | Treated Wooden Poles 9m | 2018-02-01 | Engineering Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Nzima | 2018-02-05 | 2018-02-08 | 2018-02-09 | Fail | 28000 | Reported | 8 | 4 |  |  | 188 | Dispose
166 | IQS-I/18/106 | Imports |  |  |  | Treated Wooden Poles 9m | 2018-02-01 | Engineering Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Nzima | 2018-02-05 | 2018-02-08 | 2018-02-09 | Fail | 28000 | Reported | 8 | 4 |  |  | 188 | Dispose
167 | IQS-I/18/107 | Imports |  |  |  | Treated Wooden Poles 9m | 2018-02-01 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Nzima | 2018-02-05 | 2018-02-08 | 2018-02-09 | Fail | 28000 | Reported | 8 | 4 |  |  | 188 | Dispose
168 | IQS-I/18/109 | Imports |  |  |  | Treated Wooden Poles | 2018-02-01 | Chemical Technology Division |  | Normal | Non-Building | Wooden Poles | Blantyre | Nzima | 2018-02-05 | 2018-02-08 | 2018-02-09 | Fail | 28000 | Reported | 8 | 4 |  |  | 188 | Dispose
169 | MS/18/002A | Complaint |  |  |  | Constron Cement | 2018-02-01 | Food Technology Division |  | Express | Building | Cement | 32.5N | Barnaba | 2018-02-02 | 2018-02-02 |  |  |  | In Progress | 188 | 1 |  |  | 188 | Pending
170 | MS/18/002B | Complaint |  |  |  | CM | 2018-02-01 | Chemical Technology Division |  | Express | Building | Cement | 32.5N | Barnaba | 2018-02-02 | 2018-02-02 |  |  |  | In Progress | 188 | 1 |  |  | 188 | Pending
171 | IQS/18/234 | Imports |  |  |  | Tembo Superset Cement | 2018-02-01 | Food Technology Division |  | Normal | Building | Cement | 42.5N | Gwaza | 2018-03-01 |  |  |  |  | Not Done | 188 | 28 |  |  | 188 | Pending
172 | IQS/18/235 | Imports |  |  |  | Tembo Superset Cement | 2018-02-01 | Engineering Technology Division |  | Normal | Building | Cement | 42.5N | Gwaza | 2018-03-01 |  |  |  |  | Not Done | 188 | 28 |  |  | 188 | Pending
173 | IQS/18/233 | Imports |  |  |  | Tembo Superset Cement | 2018-02-01 | Food Technology Division |  | Normal | Building | Cement | 42.5N | Gwaza | 2018-03-01 |  |  |  |  | Not Done | 188 | 28 |  |  | 188 | Pending
174 | IQS/18/258 | Imports |  |  |  | Nugget Shoe Polish | 2018-02-02 | Chemical Technology Division |  | Normal | Non-Building | Shoe Polish |  | Nzima | 2018-02-06 | 2018-02-06 | 2018-02-07 | pass | 13000 | Reported | 5 | 4 |  |  | 187 | Dispose
175 | IQS/18/354 | Imports |  |  |  | Baby Soft 2 Ply toilet tissue | 2018-02-02 | Food Technology Division |  | Normal | Non-Building | Toilet Tissue |  | Andrew Matrauza | 2018-02-06 | 2018-02-06 | 2018-02-07 | pass | 12200 | Reported | 5 | 4 |  |  | 187 | Dispose
176 | IQS/18/229 | Imports |  |  |  | 12mm Deformed Bars | 2018-02-05 | Engineering Technology Division |  | Normal | Building | Steel Bars |  | Barnaba | 2018-02-07 | 2018-02-23 | 2018-02-26 | pass | 14000 | Reported | 21 | 2 |  |  | 184 | Dispose
177 | IQS/18/228 | Imports |  |  |  | 6mm Round Bar Hot Rolled | 2018-02-05 | Food Technology Division |  | Normal | Building | Steel Bars |  | Barnaba | 2018-02-07 | 2018-02-23 | 2018-02-26 | pass | 2800 | Reported | 21 | 2 |  |  | 184 | Dispose
178 | IQS/18/231 | Imports |  |  |  | 16mm Deformed Bars | 2018-02-05 | Engineering Technology Division |  | Normal | Building | Steel Bars |  | Barnaba | 2018-02-07 | 2018-02-23 | 2018-02-26 | pass | 14000 | Reported | 21 | 2 |  |  | 184 | Dispose
179 | C/051 | Complaint |  |  |  | Duracrete Cement | 2018-02-05 | Food Technology Division |  | Express | Building | Cement | 32.5N | Barnaba | 2018-02-21 | 2018-02-21 |  |  |  | In Progress | 184 | 16 |  |  | 184 | Pending
180 | IQS/18/230 | Imports |  |  |  | 8mm Round Bars | 2018-02-06 | Engineering Technology Division |  | Normal | Building | Steel Bars |  | Barnaba | 2018-02-07 | 2018-02-23 | 2018-02-26 | Pass | 2800 | Reported | 20 | 1 |  |  | 183 | Dispose
181 | IQS/18/226 | Imports |  |  |  | 10mm Round Bar Hot Rolled | 2018-02-06 | Food Technology Division |  | Normal | Building | Steel Bars |  | Barnaba | 2018-02-07 | 2018-02-23 | 2018-02-26 | pass | 2800 | Reported | 20 | 1 |  |  | 183 | Dispose
182 | IQS/18/269 | Imports |  |  |  | Mphamvu Cement | 2018-02-06 | Engineering Technology Division |  | Normal | Building | Cement | 42.5R | Gwaza | 2018-03-01 |  |  |  |  | Not Done | 183 | 23 |  |  | 183 | Pending
183 | IQS/18/270 | Imports |  |  |  | Supaset Cement | 2018-02-06 | Food Technology Division |  | Normal | Building | Cement | 32.5N | Mhango | 2018-02-12 |  |  |  |  | Not Done | 183 | 6 |  |  | 183 | Pending
184 | IQS/18/233B | Imports |  |  |  | Curzon School Shoe | 2018-02-07 | Engineering Technology Division |  | Normal | Non-Building | Mens shoes with stuck non outer soles | size 2 | Nzima | 2018-02-08 | 2018-02-08 | 2018-02-09 | pass | 6300 | Reported | 2 | 1 |  |  | 182 | Dispose
185 | CIS/18/42 | Certification |  |  |  | Yowala Candles | 2018-02-07 | Food Technology Division |  | Normal | Non-Building | candles | 37.5G | Nzima | 2018-02-08 | 2018-02-08 | 2018-02-09 | pass | 10700 | Reported | 2 | 1 |  |  | 182 | Dispose
186 | MAT/18/AV/03 | Clientele |  |  |  | Compressive & Density | 2018-02-08 | Chemical Technology Division |  | Express | Building | Concrete Blocks | JOGS | Mhango | 2018-02-09 |  |  |  |  | Not Done | 181 | 1 |  |  | 181 | Pending
187 | MAT/18/AV/04 | Clientele |  |  |  | Compressive Strength | 2018-02-08 | Chemical Technology Division |  | Express | Non-Building | Limestone | Rift Valley Mining | Mhango | 2018-02-09 |  |  |  |  | Not Done | 181 | 1 |  |  | 181 | Pending
188 | IQS/18/387 | Imports |  |  |  | Checkers Toilet Paper | 2018-02-13 | Chemical Technology Division |  | Normal | Non-Building | Toilet Tissue |  | Nzima | 2018-02-13 | 2018-02-13 | 2018-02-16 | pass | 12200 | Reported | 3 | 0 |  |  | 176 | Dispose
189 | IQS/18/681 | Imports |  |  |  | Angel Khasu | 2018-02-15 | Food Technology Division |  | Normal | Non-Building | Agricultural Hoe |  | Nzima | 2018-02-19 | 2018-02-19 | 2018-02-22 | pass | 6900 | Reported | 7 | 4 |  |  | 174 | Dispose
190 | IQS/18/405 | Imports |  |  |  | N70 Lead Acid Batteries | 2018-02-13 | Chemical Technology Division |  | Normal | Non-Building | Lead Acid Batteries | N70/12/SBR nf 650 | Nzima | 2018-02-14 | 2018-02-14 | 2018-02-16 | Pass | 20200 | Reported | 3 | 1 |  |  | 176 | Dispose
191 | IQS/18/404 | Imports |  |  |  | N50 Lead Acid Batteries | 2018-02-13 | Food Technology Division |  | Normal | Non-Building | Lead Acid Batteries | N50/12/SBL Battery | Nzima | 2018-02-14 | 2018-02-14 | 2018-02-16 | Pass | 20200 | Reported | 3 | 1 |  |  | 176 | Dispose
192 | [5 empty] | Cleaning Laboratory |  | Engineering Technology Division |  |  |  | General Cleaning |  | Barnaba | 2018-02-17 | 2018-02-17 | 2018-02-17 |  |  | Reported |  |  |  |  | 43320 | Dispose
193 | [5 empty] | Cleaning Laboratory | 2018-06-10 | Food Technology Division |  |  |  | General Cleaning |  | Barnaba | 2018-02-18 | 2018-02-18 | 2018-02-18 |  |  | Reported | -112 | -112 |  |  | 59 | Dispose
194 | IQS/18/473 | Imports |  |  |  | Lion Blck shoe Polish | 2018-02-19 | Engineering Technology Division |  | Normal | Non-Building | Shoe Polish |  | Nzima | 2018-02-19 | 2018-02-20 | 2018-02-21 | Pass | 13000 | Reported | 2 | 0 |  |  | 170 | Dispose
195 | IQS-I/18/096 | Imports |  |  |  | Treated Wooden Poles 11m | 2018-01-31 | Chemical Technology Division |  | Normal | Non-Building | Wooden Poles | Lilongwe | mhango | 2018-02-05 | 2018-02-13 | 2018-02-19 | Pass | 28000 | Reported | 19 | 5 |  |  | 189 | Dispose
196 | AV 954-1 | Clientele |  |  |  | Duracrete Cement - China Railways | 2018-02-19 | Food Technology Division |  | Normal | Building | Cement | 32.5N | Nzima | 2018-02-21 | 2018-02-21 |  |  |  | In Progress | 170 | 2 |  |  | 170 | Pending
197 | AV 954-2 | Clientele |  |  |  | Tembo Superset Cement - China Railways | 2018-02-19 | Engineering Technology Division |  | Normal | Building | Cement | 42.5N | Nzima | 2018-02-21 | 2018-02-21 |  |  |  | In Progress | 170 | 2 |  |  | 170 | Pending
198 | AV 955-1 | Clientele |  |  |  | 32mm Steel Bars | 2018-02-19 | Chemical Technology Division |  | Normal | Building | Steel Bars | China Railway | Nzima | 2018-02-20 | 2018-02-21 | 2018-02-23 | Pass | 190011.5 | Reported | 4 | 1 |  |  | 170 | Dispose
199 | AV 955-2 | Clientele |  |  |  | 25mm Steel Bars | 2018-02-19 | Food Technology Division |  | Normal | Building | Steel Bars | China Railway | Nzima | 2018-02-20 | 2018-02-21 | 2018-02-23 | Pass |  | Reported | 4 | 1 |  |  | 170 | Dispose
200 | AV 955-3 | Clientele |  |  |  | 20mm Steel Bars | 2018-02-19 | Engineering Technology Division |  | Normal | Building | Steel Bars | China Railway | Nzima | 2018-03-26 | 2018-02-21 | 2018-02-23 | Pass |  | Reported | 4 | 35 |  |  | 170 | Dispose
201 | AV 955-4 | Clientele |  |  |  | 16mm Steel Bars | 2018-02-19 | Chemical Technology Division |  | Normal | Building | Steel Bars | China Railway | Nzima | 2018-03-16 | 2018-02-21 | 2018-02-23 | Pass |  | Reported | 4 | 25 |  |  | 170 | Dispose
202 | AV 955-5 | Clientele |  |  |  | 12mm Steel Bars | 2018-02-19 | Food Technology Division |  | Normal | Building | Steel Bars | China Railway | Nzima | 2018-03-19 | 2018-02-21 | 2018-02-23 | Pass |  | Reported | 4 | 28 |  |  | 170 | Dispose
203 | AV 955-6 | Clientele |  |  |  | 10mm Steel Bars | 2018-02-19 | Chemical Technology Division | Pesticides | Normal | Building | Steel Bars | China Railway | Nzima | 2018-03-18 | 2018-02-21 | 2018-02-23 | Pass |  | Reported | 4 | 27 |  |  | 170 | Dispose
204 | AV 955-7 | Clientele |  |  |  | 8mm Steel Bars | 2018-02-19 | Food Technology Division |  | Normal | Building | Steel Bars | China Railway | Nzima | 2018-02-20 | 2018-02-21 | 2018-02-23 | Pass |  | Reported | 4 | 1 |  |  | 170 | Dispose
205 | CIS/17/2064 | Certification |  |  |  | Hydrated Lime | 2018-02-20 | Chemical Technology Division |  | Express | Building | Lime |  | Nzima | Sample not provide yet |  |  |  |  | Not Done | 169 | 169 |  |  | 169 | Pending
206 | CIS/18/70 | Certification |  |  |  | UPVC Pipes 63mm Class 10 | 2018-02-20 | Food Technology Division |  | Normal | Non-Building | UPVC | Class 10 | Nzima | pending |  |  |  |  | Not Done | 169 | 169 |  |  | 169 | Pending
207 | CIS/18/69 | Certification |  |  |  | UPVC Pipes 50mm Class 10 | 2018-02-20 | Engineering Technology Division | Engineering & Materials | Normal | Non-Building | UPVC | Class 10 | Nzima | pending |  |  |  |  | Not Done | 169 | 169 |  |  | 169 | Pending
208 | IQS/18/514 | Imports |  |  |  | Blank Number Plates - Yellow | 2018-02-23 | Food Technology Division |  | Express | Non-Building | Number Plates | 444x120 | Nzima | 2018-02-26 | 2018-02-26 |  |  |  | In Progress | 166 | 3 |  |  | 166 | Pending
209 | IQS/18/513 | Imports |  |  |  | Blank Number Plates - Yellow | 2018-02-23 | Engineering Technology Division | ISSU | Express | Non-Building | Number Plates | 250x105 | Nzima | 2018-02-26 | 2018-02-26 |  |  |  | In Progress | 166 | 3 |  |  | 166 | Pending
210 | IQS/18/512 | Imports |  |  |  | Number Plate - Yellow | 2018-02-23 | Food Technology Division |  | Express | Non-Building | Number Plates | 340x180 | Nzima | 2018-02-26 | 2018-02-26 |  |  |  | In Progress | 166 | 3 |  |  | 166 | Pending
211 | IQS/I/18/151 | Imports |  |  |  | Treated Wooden Poles | 2018-02-26 | Chemical Technology Division |  | Normal | Non-Building | Wooden Poles | Lilongwe | Gwaza | 2018-03-02 |  |  |  |  | Not Done | 163 | 4 |  |  | 163 | Pending
212 | IQS/I/18/127 | Imports |  |  |  | Treated wooden Poles | 2018-02-26 | Food Technology Division |  | Normal | Non-Building | Wooden Poles | Lilongwe | Gwaza | 2018-03-27 |  |  |  |  | Not Done | 163 | 29 |  |  | 163 | Pending
213 | [7 empty] | Engineering Technology Division | [16 empty] | 43320 | Pending
214 | [7 empty] | Chemical Technology Division | [16 empty] | 43320 | Pending
215 | [7 empty] | Food Technology Division | [16 empty] | 43320 | Pending
216 | [7 empty] | Engineering Technology Division | [16 empty] | 43320 | Pending
217 | [7 empty] | Chemical Technology Division | [16 empty] | 43320 | Pending
218 | [24 empty] | 43320 | Pending
219 | [24 empty] | 43320 | Pending
220 | [24 empty] | 43320 | Pending
221 | [24 empty] | 43320 | Pending
222 | [24 empty] | 43320 | Pending
223 | [24 empty] | 43320 | Pending
224 | [24 empty] | 43320 | Pending
225 | [24 empty] | 43320 | Pending
226 | [24 empty] | 43320 | Pending
227 | [24 empty] | 43320 | Pending
228 | [24 empty] | 43320 | Pending
229 | [24 empty] | 43320 | Pending
230 | [24 empty] | 43320 | Pending
231 | [24 empty] | 43320 | Pending
232 | [24 empty] | 43320 | Pending
233 | [24 empty] | 43320 | Pending
234 | [24 empty] | 43320 | Pending
235 | [24 empty] | 43320 | Pending
236 | [24 empty] | 43320 | Pending
237 | [24 empty] | 43320 | Pending
238 | [24 empty] | 43320 | Pending
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
Formulas:
Sample Residence (Days) = IF([Date Received]="","",IF([Report Date]="",TODAY()-[Date Received],[Report Date]-[Date Received]))
Sample In-Active Period (Days) = IF([Date Received]="","",IF(ISTEXT([Planned Task Date]),TODAY()-[Date Received],IF([Planned Task Date]="",TODAY()-[Date Received],[Planned Task Date]-[Date Received])))
Note on P59: Bill Gwaza: Bill Gwaza: Test date was changed from 8 Jan 17 to 17 Jan 18 due to distilled water problems that week
Note on B141: Bill Gwaza: 2 Day test only, refer to correspondence folder

## Task Statistics
General Statistics - Materials Laboratory
Personnel Work Statistics (Totals) |  |  | General Reporting Statistics
Name | No. Tasks Assigned | Percentage | Item | No. of Tasks | Percentage
Gwaza | 10 | 4.854% | Reported | 138 | 66.99%
Nzima | 40 | 19.42% | In Progress | 24 | 11.65%
Mhango | 68 | 33.01% | Not Done | 48 | 23.3%
Barnaba | 69 | 33.5% | Total No. of Tasks | 206 | 100%
Liyaya | 8 | 3.883% | Total Amount (Mwk) |  | 22600589.93
Makiyi | 7 | 3.398%
Molande | 4 | 1.942% | DIVISIONAL STATISTICS
Tech 1 | 2 | 0.9709% | Division |  | Samples Received | Reported | Backlog
Tech 2 | 1 | 0.4854% | Engineering Technology Division |  | 81 | 55 | 26
Tech 3 | 0 | 0% | Food Technology Division |  | 76 | 46 | 30
Tech 4 | 0 | 0% | Chemical Technology Division |  | 60 | 37 | 23
Tech 5 | 0 | 0%
Tech 6 | 0 | 0% | SECTIONAL STATISTICS
Tech 7 | 0 | 0% | Section |  | Sample Received | Reported | Backlog
Tech 8 | 0 | 0% | Engineering & Materials |  | 25 | 18 | 7
Tech 9 | 0 | 0% | ISSU |  | 21 | 10 | 11
Tech 10 | 0 | 0% | Microbiology |  | 16 | 7 | 9
Tech 11 | 0 | 0% | Pesticides |  | 6 | 3 | 3
Tech 12 | 0 | 0% | Petrochemicals |  | 7 | 6 | 1
Tech 13 | 0 | 0% | General Chemistry |  | 17 | 9 | 8
Total No. of Samples/Tasks | 206 | 100% | Food |  | 20 | 13 | 7

## Monthly Forecast View
Monthly Task Forecast - Materials Laboratory
Tasks Per Technician
Date | Total Tasks | Gwaza | Nzima | Mhango | Barnaba | Liyaya | Makiyi | Molande | Tech 1 | Tech 2 | Tech 3 | Tech 4 | Tech 5 | Tech 6 | Tech 7 | Tech 8 | Tech 9 | Tech 10 | Tech 11 | Tech 12
2018-08-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-09-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-09-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-09-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-09-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-09-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-09-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Monthly Backcast View
Monthly Task Forecast - Materials Laboratory
Enter Start Date: | 2018-01-01
Tasks Per Technician
Date | Total Tasks | Gwaza | Nzima | Mhango | Barnaba | Liyaya | Makiyi | Molande | Tech 1 | Tech 2 | Tech 3 | Tech 4 | Tech 5 | Tech 6 | Tech 7 | Tech 8 | Tech 9 | Tech 10 | Tech 11 | Tech 12
2018-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-04 | 4 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-05 | 8 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-06 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-07 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-09 | 15 | 1 | 0 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-10 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-11 | 7 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-12 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-16 | 9 | 0 | 1 | 7 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-17 | 3 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-18 | 15 | 0 | 2 | 10 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-19 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-20 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-21 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-24 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-25 | 9 | 1 | 0 | 7 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-26 | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-27 | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-29 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0